## MPPR- ACT-117C (p5)
ACT-117C (Reb. 03/2020)
Goverment of Puerto Rico
Department of Transportation and Public Works
HIGHWAY AND TRANSPORTATION AUTHORITY
MONTHLY PROGRESS PAYMENT REPORT
1. To: |  | Director Ejecutivo |  |  |  |  | 9. Date: |  | 2023-03-01
2. Project Name: |  | Highway Safety Improvement Highway PR 176 Kilometers 0 to 4.00 San Juan, Puerto Rico |  |  |  |  | 10. Cert. Num.: |  | 8
3. Contractor: |  | Puerto Rico Asphalt |  |  |  |  | 11. Work Performed up to: |  | 2023-02-20
4. Project Num.: |  | AC017630 |  |  |  | 12. Contract Beginning Date: |  |  | 2021-06-01
5. Federal Num.: |  | ZP-176(3) |  |  |  | 13. Contract Completion Date: |  |  | 2022-07-25
6. Oracle Num.: |  | F000176030 |  |  |  | 14. Revised Completion Date |  |  | 2022-09-08
7. Contract Num.: |  | 2021-000339 |  |  |  | 15. Project Original Amount: |  |  | 3137499
8. Municipality: |  | San Juan |  |  |  | 16. Project Revised Amount: |  |  | 4027901
17 | 18 | 19 | 20 | 21 |  |  | 22 | 23 | 24 | 25
Item No. | Alt | Spec. Code | % Federal Participation | Description |  |  | Unit | Quantity | Unit Price | Amount
108 |  | 654-531 |  | Pedestrian Signal Head 16x18 LED Configuration |  |  | Each | 19 | 940
114 |  | 654-644 |  | Coaxial and Power Cable |  |  | LnM | 300 | 11
116 |  | 654-647 |  | Traf Signal Support S Mast ARM 25 FT Galv Steel |  |  | Each | 2 | 8000
119 |  | 654-670 |  | Adv TS Cont Assemb NEMA Int/NTCIP Full |  |  | Each | 4 | 27000
132 |  | 962-012 |  | Warm Mix Asphalt Paveent Marshall S(75)(12) |  |  | Each | 3307.06 | 130
134 |  | 962-033 |  | Control Strip Section |  |  | Ton | 296.33 | 130
139 |  | 635-218 |  | Prepa Standard Underground URD-4 |  |  | Each | 5 | 1560
140 |  | 956-140 |  | Cleaning of Pull Box |  |  | Each | 34 | 272
141 |  | 888-000 |  | Special and additional Work (Grout Concrete) |  |  | LS | 100 | 112
Under penalty of absolute nullity, I hereby certify that no public servant of the Puerto Rico Highways and Transportation Authority is a party to or has an interest of any kind in the profits or benefits to be obtained under the contract which is the basis of this invoice, and should he be a party to, or have an interest in, the profits or benefits to be obtained under the contract, a waiver has been previously issued. The only consideration to provide the contracted goods or services under the contract is the payment agreed upon with the authorized representative of the government entity. The amount that appears in the invoice is fair and correct. The work has been performed, the goods have been delivered, and the services have been rendered, and no payment has been received therefor. Contractor:__________________________________________________________
PAGE 5
26. Work Performed (WP):
39.Prepared by: |  |  | Christie Mota Vélez/ Puerto Rico Asphalt, LLC |  |  |  |  | 27. 5% Retained (WP):
|  |  | Contractor |  |  | Date |  | 28. Reimbursement (WP)(+): |  | 0
40. Concurred by: |  |  | Ing. Luis R. Pastor Reyes |  |  |  |  | 29. Sub Total:
|  |  | Project Administrator or Resident Engineer or Inspector |  |  | Date |  | 30. Material on Site (+/-): |  | -63897.5
41. Received for Review: | [7 empty] | 31. Liquidated Damages (LQD)(-):
|  |  | Regional Director's Designated Representative |  | Prompt Payment Process Start Date |  |  | 32. Reimbursement (LqD)(+): |  | 0
42. Submitted for Review: |  |  | Ing. Carlos Céspedes Gómez |  |  |  |  | 33. Extra Retainage (+/-): |  | 0
|  |  | Area Supervisor (Program Manager) |  | Date |  |  | 34. Price Adjustment Clause (+/-): |  | 0
43. Approved by: |  |  | Ing. Eduardo F. Ruiz Vélez |  |  |  |  | 35. Safety Penalties - Spec 638(-): |  | 0
|  |  | Regional Director |  |  | Date |  | 36. Other (+/-): |  | 0
44. Approved for Payment by: |  |  | Sr. Angel M. Félix Cruz |  |  |  |  | 37. Net Payment:
|  |  | Finance Area Director |  |  | Date |  | 38. Total to Date (WP):
45. Percent Work Performed:
46. Percent Time

## ACT-117C PAG atrás
LIQUIDATED DAMAGES - N/A
| For not completing project on contract time from: | [5 empty] | 2022-09-09 |  | to | 2023-02-20 | both dates included
[7 empty] | 47 |  |  | 48
| a total of | 164 |  | days at | 2000 | per day. |  |  | 3 | Total to Date:
|  | 49 |  |  | 50 | [5 empty] | 51
| Previous Date: |  | 0 | [5 empty] | This Period: |  | 370000
|  |  | 52 | [7 empty] | 53
REIMBURSEMENT - N/A
| For extension of Contract Time this period: | [6 empty] | days at |  |  | per day
[6 empty] | 54 |  |  |  | 55
This Period:
56
| Previous Date: | [8 empty] | Total to Date:
1 | [6 empty] | LS
36 | 59. Remarks
90
101
60. Distribution
|  |  |  | ORIGINAL | Treasury Office |  |  | COPY 3 |  | Project
|  |  |  | COPY 1 | Preaudit Office |  |  | COPY 4 |  | Construction Area
|  |  |  | COPY 2 | Contractor