## CML Report
Ver: 11.29.2021
Construction Contract Modification Log
General Information: | [10 empty] | Legend: |  |  | Contract Time Information:
Project Number: |  |  | AC-017630 | [7 empty] | White cells, project administrator will provide project information (input cells). |  |  | Contract Beginning Date: |  |  |  | 2021-06-01
Federal Number: |  |  | ZP-176(3) | [10 empty] | Original Contract Time: |  |  |  | 420
Oracle Number: |  |  | F000176030 | [7 empty] | Color cells, the excel file will make calculations (formula cells). |  |  | Original Termination Date:
Project Tittle: |  |  | Highway Safety Improvements Highway PR-176, km 0.00 to 4.00 San Juan, PR | [10 empty] | Total Time Extensions (Days):
Contractor : |  |  | Puerto Rico Asphalt, LLC | [7 empty] | Gray cells & Blue Font Color, attention is required (see comment in the cells). |  |  | Revised Termination Date:
Project Manager: |  |  | Ing. Luis R. Pastor Reyes | [10 empty] | Change in Contract Time (%):
Date: |  |  | 2024-05-16 | [7 empty] | Red Cells, possible action by PRHTA (red flag). |  |  | Time Completed to Date (%):
[11 empty] | Red Font Color are for negative numbers or quantities. |  |  | Change in Contract Amount (%):
Has the project reached substantial completion? | [5 empty] | Y/N? | NO | [6 empty] | % Work Performed to Date: |  |  |  | 40%
No. of CHO documents: |  |  | 4 | [10 empty] | Estimated Completion Date: |  |  |  | 2022-07-25
No. of EWO documents: |  |  | 6 | [10 empty] | Administrative Date of Comptroller Office (Contralor): |  |  |  | 2024-09-07
[14 empty] | Project End Date (FMIS): |  |  |  | 2023-08-07
Project Description: |  |  | This project is located on Highway PR-176 from kilometer 0.00 to 4.00 for total length of 4 km. The Pavement Rehabiltation and Safety Improvement Project for PR-176, commences at its intersection with PR-1 and continue along the exixting highway up to the intersection with PR-199 in the municipality of San Juan. The proposed works consist of the improvements to the exixting roadside safety elements at highway PR-176. The works to be performed also include: maintenance and protection of traffic, cold milling and placement of bituminous pavement, the aplication thermoplastic pavement marking, installation of traffic signs, removal, storage and delivered of exixting guard rail, furnishing and installation of Wbeam guard rail single face and double face, contruction of new transition modules traffic signals and other miscellaneous works as shown on plans.
NOTES:
Is this project eligible for toll credits? | [5 empty] | Y/N? | YES |  | 1- Examples of projects that are not eligible for toll credits (answer to the question is NO): ER Projects and Old Projects without Toll Credits.
Does the project have pay items with ER funds? | [5 empty] | Y/N? | NO
Original Project Funds Information
Units | Federal Share % |  | INPUT PROJECT AGREEMENT | [5 empty] | FEDERAL FUNDS |  |  |  | STATE FUNDS
|  |  | Participating |  | Contingencies (Participating) |  | Payroll, Mileage and Diets |  | F.A. Funds Requested | Contingencies (Federal Funds) | Calculation of Toll Credits | Contingencies (Toll Credits) | State Share of Federal Funds | Contingencies (State Share) | Not Participating (State Funds) | Contingencies (Not Participating) |  | Payroll, Mileage and Diets
Unit 1 |  |  | 1937696 |  | 193769.6 |  |  |  | 1710501.14 | [5 empty] | 58670 | 5867
Unit 2 |  |  | 44161 |  | 4416.1 |  |  |  | 48577.1 | [5 empty] | 0 | 0
Unit 3 |  |  | 218354 |  | 21835.4 |  |  |  | 240189.4 | [5 empty] | 0 | 0
Unit 4 |  |  | 858618 |  | 85861.8 |  |  |  | 757945.03 | [5 empty] | 20000 | 2000
Unit 5
Unit 6
Unit 7
Unit 8
Unit 9
Unit 10
Unit 11
Unit 12
Unit 13
Unit 14
Unit 15
Unit 16
Unit 17
Unit 18
Unit 19
Unit 20
Unit 21
Unit 22
Unit 23
Unit 24
Unit 25
Sub Totals
Totals
Eng. Contract Estimate: | [5 empty] | This is the original cost of the project (bid process).
Total Construction Cost: | [5 empty] | This is the total budget for the project. Includes federal and state funds, contingencies, and payroll or expenses when applicable.
NOTE:
1- IF THE FEDERAL SHARE % COLUMN HAS VALUES DIFFERENT THAN 80.25%, 90% AND 100%, VERIFY THE INFORMATION INCLUDED IN THE TABLE BEFORE CONTINUING WITH THE PROCESS.
Project Modification Documents
Document # |  | Proposed Amount |  |  | Federal Share (%) | Federal Share Amount |  |  | Toll Credits Amount | Non Participating Amount (State Funds) | State Share of Federal Funds | Time Extension (Days) | Federal Share for Project Modification Letter | Toll Credits for Project Modification Letter | Comments
CHO | EWO | [17 empty] | Fed Share | Cumm Invertido | Add Funds - Cumm | Determine Funds | Toll Credits | Cumm Invertido | Add Funds - Cumm | Determine Funds
| 1 | 6000 |  |  | 0%
1 |  | -73400 |  |  | 80.25%
1 |  | 108000 |  |  | 80.25%
| 2 | 450000 |  |  | 0%
| 3 | 24044 |  |  | 80.25% | [6 empty] | 25
| 3 | 9248 |  |  | 0%
2 |  | 366510 |  |  | 80.25% | [6 empty] | 20
3 |  | 48200 | [9 empty] | 154
| 4 | 1479970
| 5 | 48473
| 6 | 618332
4 |  | 185100
[20 empty] | 0 | 0 |  |  | 0 | 0
[6 empty] | Federal Share |  |  | Toll Credits | State Funds |  | Time Extension | Federal Share for Project Modification Letter | Toll Credits for Project Modification Letter
Modification Total Amount: | [5 empty] | Comparison of Modifications with Project Contingencies: |  |  |  | Federal |  |  | Toll Credits |  | State |  |  |  | Federal | Toll Credits | State
Revised Contract Amount (all Funds): | [5 empty] | Does Contract Modification Exceed Contingencies? | [12 empty] | Federal Funds Needed:
Amount of Federal Funds Needed (FMIS): | [5 empty] | NOTE: PRHTA FEDERAL LIAISON OFFICE AND BUDGET OFFICE WILL VERIFY THE VALUES IN THE CELLS OF FEDERAL, TOLL CREDITS AND STATE FUNDS TO IDENTIFY THE NEED FOR ADDITIONAL FUNDS IN THE PROJECT.
Amount of State Funds Needed (FMIS):
AS INDICATED IN THE PROJECT MODIFICATION REQUEST LETTERS (THE LETTERS ARE DEVELOPED BY THE PRHTA FEDERAL LIAISON OFFICE AND EVALUATED/APPROVED BY THE FHWA PR/USVI DIVISION. FUNDS INFORMATION IN THE LETTERS WILL BE ACCESSED THROUGH A FOLDER IN A CLOUD PLATFORM):
Obligations Amount (excludes Payroll, Mileage and Diets) |  |  |  | Total Cost |  |  |  | Federal Funds |  | Federal Share |  |  | Toll Credits |  | State Funds
Original Project Funds
Modification #1 | [9 empty] | 0 |  |  | 0 |  | 448133
Modification #2
Modification #3
Modification #4
Modification #5
Modification #6
Modification #7
Modification #8
Modification #9
Modification #10
Modification #11
Modification #12
Modification #13
Modification #14
Modification #15
Modification #16
Modification #17
Modification #18
Modification #19
Modification #20
Modification #21
Modification #22
Modification #23
Modification #24
Modification #25
Modification #26
Modification #27
Modification #28
Modification #29
Modification #30
Modification #31
Modification #32
Modification #33
Modification #34
Modification #35
Modification #36
Modification #37
Modification #38
Modification #39
Modification #40
Modification #41
Modification #42
Modification #43
Modification #44
Modification #45
Modification #46
Modification #47
Modification #48
Modification #49
Modification #50
Modification #51
Modification #52
Modification #53
Modification #54
Modification #55
Modification #56
Modification #57
Modification #58
Modification #59
Modification #60
Modification #61
Modification #62
Modification #63
Modification #64
Modification #65
Modification #66
Modification #67
Modification #68
Modification #69
Modification #70
Modification #71
Modification #72
Modification #73
Modification #74
Modification #75
Modification #76
Modification #77
Modification #78
Modification #79
Modification #80
Modification #81
Modification #82
Modification #83
Modification #84
Modification #85
Modification #86
Modification #87
Modification #88
Modification #89
Modification #90
Modification #91
Modification #92
Modification #93
Modification #94
Modification #95
Modification #96
Modification #97
Modification #98
Modification #99
Modification #100
Modification #101
Modification #102
Modification #103
Modification #104
Modification #105
Modification #106
Modification #107
Modification #108
Modification #109
Modification #110
Modification #111
Modification #112
Modification #113
Modification #114
Modification #115
Modification #116
Modification #117
Modification #118
Modification #119
Modification #120
Modification #121
Modification #122
Modification #123
Modification #124
Modification #125
Modification #126
Modification #127
Modification #128
Modification #129
Modification #130
Modification #131
Modification #132
Modification #133
Modification #134
Modification #135
Modification #136
Modification #137
Modification #138
Modification #139
Modification #140
Modification #141
Modification #142
Modification #143
Modification #144
Modification #145
Modification #146
Modification #147
Modification #148
Modification #149
Modification #150
Revised Amount
Note on T8: Nota: Incluir la fecha de comienzo del contrato en el siguiente formato: MM/DD/YYYY.
Note on T9: Nota: Incluir el número original de días para completar el proyecto.
Note on T13: Nota: Si el fondo del encasillado es rojo, la modificación es considerada un cambio mayor (SOP).
Note on E14: Nota: Fecha del informe mensual o del documento (CHO o EWO) donde se incluye el Modification Log. Incluir en el siguiente formato: MM/DD/YYYY
Note on T14: Nota: Este % del proyecto es a la fecha del informe.
Note on T15: Nota: Si el fondo del encasillado es rojo, la modificación es considerada un cambio mayor (SOP).
Note on T16: Nota: El % de trabajo realizado en el campo.
Note on E17: Nota: Número de CHOs en el proyecto incluyendo el documento a ser incluido en este informe.
Note on T17: Nota: Terminación real del proyecto. Fecha que el administrador estima terminará el proyecto. Entre en el siguiente formato: MM/DD/YYYY
Note on E18: Nota: Número de EWOs en el proyecto incluyendo el documento a ser incluido en este informe.
Note on T18: Nota: Incluir fecha de terminación administrativa del contrato en la Oficina del Contralor. Celda con fondo rojo representa que la fecha es menor a la fecha actual.
Note on T19: Nota: Incluir fecha de terminación administrativa del contrato en el sistema financiero de FHWA, conocido como FMIS (Financial Management Information System). Celda con fondo rojo representa que la fecha es menor a la fecha actual.
Note on E22: Nota: Descripción general de los trabajos o "scope" del proyecto.
Note on B31: Nota: Para completar esta tabla se utiliza el "Project Agreement". La información se escribe directamente, no hay que hacer ningún cómputo. Si el proyecto es estatal, solamente se llenan las columnas de State Funds.
Note on E33: Nota: Entre el valor de fondos federales participativos que se encuentra en el documento "Project Agreement" al final de cada unidad. Este valor representa todas las partidas elegibles para fondos federales.
Note on G33: Nota: Entre el valor de la contigencia que se encuentra en el documento "Project Agreement" al final de cada unidad.
Note on I33: Nota: Entre el valor de fondos para "payroll, mileage and diets" que se encuentra en el documento "Project Agreement"al final de cada unidad. Los proyectos mas recientes no tienen este valor.
Note on K33: Nota: En el "Project Agreement", la penúltima página tiene una tabla de "SUMMARY OF COST". La información viene de esa tabla, en la columna que lleva el mismo nombre.
Note on L33: Nota: Este campo se calcula automáticamente con la información incluida en las columnas anteriores.
Note on M33: Nota: Este campo se calcula automáticamente con la información incluida en las columnas anteriores.
Note on N33: Nota: Este campo se calcula automáticamente con la información incluida en las columnas anteriores.
Note on O33: Nota: Este campo se calcula automáticamente con la información incluida en las columnas anteriores.
Note on P33: Nota: Este campo se calcula automáticamente con la información incluida en las columnas anteriores.
Note on Q33: Nota: Entre el valor de fondos estateles (no participativos) que se encuentra en el documento "Project Agreement" al final de cada unidad.
Note on R33: Nota: Entre el valor de la contigencia para los fondos estatales (no participativos) que se encuentra en el documento "Project Agreement" al final de cada unidad.
Note on T33: Nota: Entre el valor de fondos para "payroll, mileage and diets" que se encuentra en el documento "Project Agreement"al final de cada unidad, respecto a los fondos estatales (no participativos). Los proyectos mas recientes no tienen este valor.
Note on G68: Nota: Incluir el % de participación federal, según las partidas de pago en la modificación.
Note on H68: Nota: Este campo se calcula automáticamente con la información incluida en las columnas anteriores.
Note on K68: Nota: Este campo se calcula automáticamente con la información incluida en las columnas anteriores.
Note on L68: Nota: Este campo se calcula automáticamente con la información incluida en las columnas anteriores.
Note on M68: Nota: Este campo se calcula automáticamente con la información incluida en las columnas anteriores.
Note on O68: Nota: Este campo se calcula automáticamente con la información incluida en las columnas anteriores. Para uso de la Oficina de Enlace Federal y Presupuesto.
Note on P68: Nota: Este campo se calcula automáticamente con la información incluida en las columnas anteriores. Para uso de la Oficina de Enlace Federal y Presupuesto.
Note on Q68: Nota: Incluir comentarios sobre las modificaciones al proyecto.
Note on L226: Nota: Esta es la cantidad que excede la contingencia federal.
Note on O226: Nota: Esta es la cantidad que excede la contingencia para toll credits.
Note on Q226: Nota: Esta es la cantidad que excede la contingencia estatal, es necesario añadir fondos estatales.
Note on E227: Nota: Si el encasillado está en rojo, el proyecto requiere de fondos adicionales.
Note on E228: Nota: Si el encasillado está en rojo, el proyecto requiere de fondos adicionales.
Note on E229: Nota: Si el encasillado está en rojo, el proyecto requiere de fondos adicionales.

## Data Analysis (hidden)
Report Date | Project No. | Federal No. | Oracle No. | Project Title | Contractor | Contract Beginning Date | Original Contract Time | Original Termination Date: | Total Time Extensions (Days): | Revised Termination Date: | Change in Contract Time (%): | % of Time Completed to Date: | Change in Contract Amount (%): | % Work Performed to Date: | Estimated Completion Date: | Project End Date (FMIS): | Eng. Contract Estimate: | Total Construction Cost: | Number of CHO documents: | Number of EWO documents: | Revised Contract Amount: | Obligation Amount: | Amount of Federal Funds Needed (FMIS): | Amount of State Funds Needed (FMIS):