## Instructions
Instrucciones para Completar el Formulario ACT-YYY “Change Order”
1 | . | Nombre del proyecto, según aparece en el contrato. | 19 | . | Descripción de la partida según el Desglose de Partidas incluido en el contrato o según establecido en el Catálogo de Partidas.
2 | . | Nombre del contratista, según aparece en el contrato y en el Registro Único Licitadores (RUL) | 20 | . | Este encasillado puede asignarle una descripción adicional o un código adicional, según aplique, para identificar una misma partida que aplique a varias localidades.
3 | . | Número de proyecto (versión corta) según aparece en el contrato (código AC-XXXXXX). | 21 | . | Unidad de pago según contrato: LnM, CuM, SqM, Ton, day, etc.
4 | . | Número federal del proyecto, si aplica. De lo contrario, escribir N/A. | 22 | . | Cantidad total por partida.
5 | . | Número “Oracle” del proyecto según aparece en el contrato (número de 22 dígitos). | 23 | . | Precio unitario de contrato en la sección Contract Items. Precio unitario negociado en la sección New Items.
6 | . | Número de contrato según registrado en la Oficina del Contralor de Puerto Rico. | 24 | . | Monto total de la partida. Multiplicación de columna 22 y 23
7 | . | Se utiliza la letra de la enmienda correspondiente de acuerdo con la secuencia de los documentos registrados ante el contralor al momento de la preparación del documento. La letra "Z" no se utiliza en la secuencia de enmiendas registradas ante el Contralor. En esos casos, la secuencia continúa con "AA". | 25 | . | Indicar el % de participación federal, cuando aplique.
|  |  | 26 | . | Subtotal de partidas existentes en el contrato (suma valores en la columna 24 de la sección de Contract Items).
|  |  | 27 | . | Sub-total de las nuevas partidas creadas en este documento (suma de valores en la columna 24 de la sección de New Items.
|  |  | 28 | . | Suma total de las cantidades en los encasillados 26 y 27. En el caso de múltiples páginas, es la suma de todos los subtotales.
8 | . | Número secuencial del Change Order. | 29 | . | Suma del costo original del proyecto más todos los documentos previamente aprobados.
9 |  | Fecha de preparación del documento.
9a | . | Fecha de comienzo del proyecto según Notice to Proceed. En casos de proyectos de emergencia, la fecha debe ser la de la firma del contrato. | 30 | . | Monto revisado actual. La suma de los encasillados 28 y 29.
10 | . | Fecha de terminación contractual, según documentos aprobados. | 31 | . | Nombre y firma del Administrador y/o Ingeniero/Inspector Residente.
11 | . | Si se determina como parte del documento un aumento al tiempo del contrato, se debe indicar la cantidad de días calendario en este espacio y justificar los mismos en el encasillado 36 del documento. | 32 | . | Nombre y firma del Representante del Contratista. La persona que firma debe estar autorizada en el RUL. De no ser así deben presentar la resolución corporativa autorizando a la persona que firmara por parte del contratista.
11.a | . | De los días de extensión de tiempo otorgados en el encasillado 11, indique cuántos de ellos son compensables, de no haber días compensables indique N/A. | 33 | . | Nombre y firma del Supervisor de Proyecto/Gerente de Proyecto, Director de Distrito/Gerente de Programa y Director de la Oficina de Construcción.
12 | . | Nueva fecha de terminación (fecha proyectada incluyendo el tiempo en este documento y todas las extensiones de tiempo previamente aprobadas). | 34 | . | Nombre y firma del Director Ejecutivo en propiedad (Dirigido a la persona que aplique según la delegación de firmas) y representante de la FHWA.
13 | . | Fecha de Vigencia en el Contralor Revisada con este documento (Fecha de terminación revisada, inciso 12, más (+) 730 días) | 35 | . | Escoger el artículo bajo el cual mejor se justifique el documento. a. Diseño: omisiones o cambios relacionados al diseño del proyecto b. Construcción: cambios determinados por el Área de Construcción. c. Contrato: omisiones o cambios referentes a los documentos del contrato. Ej. Cantidades subestimadas o partidas omitidas. d. Utilidades: cualquier trabajo relacionado a utilidades de PREPA, PRASA, PRTC & CTV. e. Otros: cualquier otra razón no relacionada con las anteriores.
14 | . | Fiscal Management Information System (FMIS) Contract End Date
15 | . | Marcar todas las opciones que apliquen.
16 | . | Breve descripción del trabajo y/o las partidas incluidas en el documento incluyendo las estaciones donde se realizará el trabajo.
17 | . | Número de la partida según indicado en el Desglose de Partidas incluido en el contrato (proposal).
18 | . | Número de especificación según contrato original y/o “Extra Work Order”. Nota: En caso de que se esté creando una nueva partida con este documento, debe asegurarse que utiliza el Catálogo de Partidas Oficial de la ACT. | 36 | . | En este espacio se justificará con una explicación detallada, clara y específica la naturaleza del cambio incluyendo el tiempo adicional cuando aplique. Incluir las progresivas donde se encuentra el trabajo, cotización del Contratista en original, hojas de plano, croquis, dibujos, cómputos, foto u otra información que se entienda justifique el trabajo.
|  |  | 37 | . | Distribución de las copias de este documento

## ACT-122
|  |  |  | Government of Puerto Rico | [24 empty] | ACT-122
|  |  |  | Department of Transportation and Public Works | [24 empty] | Rev 12/2024
HIGHWAY AND TRANSPORTATION AUTHORITY
CHANGE ORDER
[20 empty] | 9. Date: |  |  |  |  | 2026-05-01
1. Project Name: |  |  |  |  | Rehabilitación de sistema de video detección (VDS) | [14 empty] | 9a. Contract Beginning Date: |  |  |  |  | 2022-11-07
2. Contractor: |  |  |  |  | Unique Builders, Inc. | [14 empty] | 10. Revised Completion Date: |  |  |  |  | 2025-08-10
3. Project Num.: |  |  |  |  | AC-200023 | [14 empty] | 11. Add Contract Time (Days): |  |  |  |  | 0
4. Federal Num.: |  |  |  |  | ER-9999(531) | [14 empty] | 11a. Compensable Days: |  |  |  |  | 0
5. Oracle Num.: |  |  |  |  | CNT116532777706200023 | [14 empty] | 12. New Completion Date: |  |  |  |  | 2025-08-10
6. Contract Num.: |  |  |  |  | 2023000161 | [14 empty] | 13. New Administrative Term Date: |  |  |  |  | 2027-08-10
7. Amendment: |  |  |  |  | G | [14 empty] | 14. FMIS End Date: |  |  |  |  | 2026-12-03
8. CHO Number.: |  |  |  |  | 4
15. Favor de marcar todas las opciones que apliquen
X |  |  | Change of Contract Items | [6 empty] | New Items (Extra Work) | [10 empty] | Time Extension
16. Description of Work/Scope of Work:
Este proyecto es uno de emergencia para reparar los daños causados por el Huracán María a las intersecciones semaforizadas, específicamente a los sistemas de cámaras de vigilancia y de monitoreo vehícular de las siguientes carreteras: PR-8, PR-23, PR-25 y PR-35.
Request is hereby made for approval of the following work to be performed in the above mentioned project. The contractor hereby agrees to perform the necessary work and furnish the necessary labor, materials and equipment that may be required by the Highway Authority and not to exceed the unit prices quoted below. The work to be performed and materials furnished shall be in accordance with the Standard Specifications of the P.R. Highway Authority and the Special Provisions applicable to the above project.
17 |  |  | 18 | 19 | [7 empty] | 20 | [5 empty] | 21 |  | 22 |  |  | 23 | 24 | [5 empty] | 25
Item Num |  |  | Item Spec. Code | Item Name (Description) | [7 empty] | Additional Information |  |  |  | Additional Code |  | Unit |  | Quantity |  |  | Unit Price | Amount | [5 empty] | % Federal
Contract Items
2 |  |  | 638-001 | Construction Signs | [13 empty] | SQM |  | -40 |  |  | 390 | -15600 | [5 empty] | 100%
3 |  |  | 638-005 | Drums | [13 empty] | EA |  | -110 |  |  | 125 | -13750 | [5 empty] | 100%
4 |  |  | 638-013 | Flashing Arrow Signs | [13 empty] | DAY |  | -450 |  |  | 19 | -8550 | [5 empty] | 100%
5 |  |  | 638-061 | Truck Mounted Attenuator (TMA) TL (3) | [13 empty] | HRS |  | -2400 |  |  | 18 | -43200 | [5 empty] | 100%
7 |  |  | 654-590 | Video Image Processor | [13 empty] | EA |  | -2 |  |  | 3300 | -6600 | [5 empty] | 100%
26 Subtotal Contract Items | [23 empty] | -87700
New Items (Extra Work)
0
0
0
27 Subtotal New Items | [23 empty] | 0 |  |  |  |  | 250000
31. Submitted by: | [6 empty] | Ing. Luis R. Pastor Reyes | [11 empty] | 28. Change Order Amount: | [5 empty] | -194007.25
[7 empty] | Project Administrator / Resident Engineer or Inspector | [5 empty] | - | Date |  |  |  |  | 29. Actual Contract Amount: | [5 empty] | 2575263.69
32. Accepted by: | [6 empty] | Ing. Domingo Polanco Espejo | [11 empty] | 30. New Contract Amount: | [5 empty] | 2381256.44
[7 empty] | Contractor | [5 empty] | - | Date
33. Recommended by: | [6 empty] | Ing. Carlos Céspedes Gómez | [11 empty] | Ing. Javier Arroyo Rosario
[7 empty] | Area Supervisor or Project Manager | [5 empty] | - | Date |  |  |  |  | Construction Office Director | [7 empty] | - | Date
Ing. Eduardo F. Ruiz Velez
[7 empty] | Distric Director or Program Manager | [5 empty] | - | Date
34. |  | Approved by: |  |  |  |  | Dr. Edwin González Montalvo
[7 empty] | Executive Director | [5 empty] | - | Date |  |  |  |  | Federal Highway Administration | [5 empty] | - | Date | - | Date
[11 empty] | Page |  |  |  | 1 | of | 8
| 1. Project Name: |  |  |  |  | Rehabilitación de sistema de video detección (VDS)
| 3. Project Num.: |  |  |  |  | AC-200023 | [15 empty] | 8. CHO Number: |  | 4
35. Reasons that justify this Change Order:
Due to:
36. Change Order Justification
Las actividades en el presente documento corresponden al proceso de liquidación parcial de las partidas.
| 37. Distribution: | [12 empty] | COPY 3 |  |  | District Office
[8 empty] | ORIGINAL | Treasury Office |  |  |  |  | COPY 4 |  |  | Project
[8 empty] | COPY 1 | Preaudit Office |  |  |  |  | COPY 5 |  |  | Construction Office
[8 empty] | COPY 2 | Contractor |  |  |  |  | COPY 6 |  |  | FHWA
[11 empty] | Page |  |  |  | 2 | of | 8
Design
Construction
Contract
Utilities
Other

## SUPP-ACT-ZZZ (hidden)
[10 empty] | Government of Puerto Rico | [17 empty] | ACT-ZZZ Rev. 06/2024
Department of Transportation and Public Works
HIGHWAY AND TRANSPORTATION AUTHORITY
Construction Area
1. Project No.
2. Oracle No.
3. Federal No.
4. Contract No.
5. OCPR Contract No.
6. Acc. No.
[21 empty] | SUPPLEMENTARY CONTRACT NO. |  |  | 7
[12 empty] | 8 | Change of Contract Items
Include New Items (Extra Work)
Time Extension
|  | This agreement entered into this | [8 empty] | Fecha del que Aprueba el CHO |  |  |  |  | 9 | by and between |  |  |  |  | Nombre del que aprueba según delegación de firmas | [7 empty] | 10 | ,
Executive Director, Highway Authority (hereinafter referred to as the Executive Director) on behalf of the Commonwealth
| of Puerto Rico; and | [5 empty] | Nombre de la Compañía | [10 empty] | 11 | Contractor, (hereinafter referred to as the Contractor).
WITNESSETH THAT:
|  | Whereas, the hereto on the | [6 empty] | Fecha del Contrato Original | [5 empty] | 13 | entered into a contract for the construction of project
| Nombre completo del Proyecto | [19 empty] | 14 | .
|  | Whereas, said parties have agreed on the performance of certain | [16 empty] | Change Order |  |  |  | 15 | at the above mentioned project.
Now, therefore, the parties hereto in consideration of the terms, covenants, agreements hereinafter contained and the
faithful performance there of hereby mutually agree as follows:
|  | First: That the Contractor agrees to perform the | [11 empty] | Change Order # | [5 empty] | 16 | at the amount of |  |  |  | $$ |  |  | 17 | and
| # días |  | 18 | additional calendar day. The Substantial Completion date is herein moved from | [21 empty] | Validar que es la vigente |  | 19 | to
| Validar que es fecha nueva |  |  |  | 20 | and the Administrative Term date is herein moved from | [15 empty] | Adm vigente |  |  | 21 | to | Adm Nueva |  | 22 | for
the contract.
Second: That all documents forming part of the original contract are also a part of this supplementary contract.
19
Name of Authorized PRHTA's Representative - Nombre del que Aprueba el CHO por delegación de firmas
Title of PRHTA's representative
Highway and Trasnportation Authority
660-43-3808
20
Name Contractor Representative
Name of Company
SSP
Correo Electrónico
Distribution |  |  |  | 23 | [10 empty] | COPY 3 |  |  | Regional Office
[6 empty] | ORIGINAL |  | Treasury Office | [6 empty] | COPY 4 |  |  | Project
[6 empty] | COPY 1 |  | Preaudit Office | [6 empty] | COPY 5 |  |  | Construction Area
[6 empty] | COPY 2 |  | Contractor | [6 empty] | COPY 6 |  |  | FHWA
Note on I11: Número de contrato asignado según registro del contralor.
Note on R23: Ivette Maldonado Hernandez:
Note on AF61: Si el representante de la compañia no está en las personas autorizadas en el RUL deben presentar la Resolución corporativa donde lo autoricen.
Note on AF63: Incluir posición del representante

## ROA (hidden)
RECORD OF AUTHORIZATION TO PROCEED WITH CONTRACT REVISION
FAX: 787-766-5924
PROJECT NO. |  | #REF! | [6 empty] | STATE NUMBER |  |  |  | STATE
#REF!
[9 empty] | #REF! |  |  |  | Puerto Rico
TYPE REVISION
| CHANGE OF CONTRACT ITEMS |  |  |  | SUPPLEMENTAL AGREEMENT | [5 empty] | TIME EXTENSION |  | SPECIFICATION CHANGE
| NEW ITEMS (EXTRA WORK) |  |  |  | OTHER |  |  | DESIGN CHANGE
REQUESTED BY: |  |  | ='CHO-ACT-XXX'!M43 | [8 empty] | DATE: | #REF!
NATURE AND REASON FOR PROPOSED REVISION (if additional space is required, use reverse side) | [14 empty] | Page 1 of 1
#REF!
Project Engineer:
Telephone Number:
Email:
Item#030 Temporary Concrete Barrier: To grant a safe pass for the traffic through the project and to guaranty the contractor and PRHTA personnel safety, we designed and recommended the construction a temporary detour to the west side of the PR-185 at Km 11.1. With the construction of the detour the amount of temporary concrete barriers increased by 134.00 LnM.
METHOD OF PAYMENT:
|  |  | INC. | DEC. |  | IN COST | $ | #REF!
ESTIMATED | [10 empty] | FORCE ACCOUNT | NEGOTIATED PRICE |  |  | LUMP SUM
|  |  | INC. | DEC. |  | IN TIME | #REF! |  |  |  | UNIT BID PRICES | OTHER:
THE WORK COVERED BY THE PROPOSED REVISION AS DESCRIBER ABOVE IS HEREBY AUTHORIZED SUBJECT TO THE CONDITIONS
MARKED BELOW:
| EVALUATION OF COST DATA | [9 empty] | AUTHORIZED WITHOUT FEDERAL PARTICIPATION
| LIMITATIONS EXTENT OF FEDERAL PARTICIPATION | [9 empty] | OTHER:
DETERMINATION OF SATISFACTORY ADJUSTMENT IN TIME
| ADEQUATE SUBMITTAL OF WRITTEN SUPPORTING DATA | [9 empty] | NONE
RECOMMENDED BY STATE ENGINEER | [9 empty] | DIVISION OFFICE APPROVAL
SIGNATURE | [5 empty] | DATE |  |  |  | SIGNATURE |  |  |  | DATE
0 | [5 empty] | #REF!
(Use reverse for comments if required)

## Table for ROA (hidden)
Item (Spec. Code) | Description | Additional Code | Unit | Quantity | Unit Price | Amount | Federal Participation %
Contract Items
New Items (Extra Work)
0

## Contralor (hidden)
5Modelo OC-08-08 (Model OC-08-08)
Rev. Octubre 1999 (Rev. October 1999)
Reglamento Núm. 33 del 28 de enero de 1998
Regulation No. 33 of January 28 1998,
ESTADO LIBRE ASOCIADO DE PUERTO RICO
Commonwealth of Puerto Rico
OFICINA DEL CONTRALOR
OFFICE OF THE COMPTROLLER OF PUERTO RICO
San Juan, Puerto Rico
CERTIFICACION
CERTIFICATION
SOBRE OTORGAMIENTO DE CONTRATO, ESCRITURA O DOCUMENTO RELACIONADO
REGARDING THE EXECUTION OF CONTRACTS DEEDS AND OTHER RELATED DOCUMENTS
1
1. | Código de Entidad
Entity Code
2. | Número del Contrato
Contract Number
3. | Fecha de Otorgamiento
Date of Execution (dd/mm/yy)
4. | Cuantía Total
Total Amount
5. | Código del Tipo del Contrato
Contract Type Code
6. | Exento
Exempt
7. | Orden (Aprobación o dispensa de algún organismo del Gobierno)
Authorization or waiver from another government entity
8. | Vigencia desde
| Effective date from | (dd/mm/aa) (dd/mm/yy) |  |  | (dd/mm/aa) (dd/mm/yy)
9. | Seguro Social Personal o Patronal |  |  | - |  |  | -
Social Security Number 8
10. | Contratista (s)
(Contractor)
11. | Representante (s) de la (s) Entidad (es) Gubernamental (es)
(Government Representative (s))
Se somete la presente certificación en cumplimiento con la Carta Circular promulgada por el Contralor de Puerto Rico
y en cumplimiento con el Reglamento Núm. 33 Sobre Registro de Contratos, Escrituras y Documentos Relacionados
y Envío de Copias a la Oficina del Contralor. Esta debe ser remitida a la Oficina del Contralor.
(This certification is submitted in compliance with the instructions issued by the Comptroller of Puerto Rico and in accordance with
Regulation No. 33, regarding the Registration of Contracts, Deeds and Other Related Documents and the Mailing of such Copies to the Comptroller's Office by the
Comptroller's Office by the government entity.)
Los suscribientes certificamos haber otorgado hoy el contrato descrito en este documento.
The undersigned, certify having that the contract described in this document was executed on this date.
12. | En (ciudad) |  | , Puerto Rico, hoy
| In |  | Purto Rico, today |  |  | (dd/mm/aa) (dd/mm/yy)
13. | Firma(s) Parte(s) Contratista(s): |  |  | 14. | Firma(s) Funcionario(s) Gubernamental(es):
| Signature of the Contractor(s): |  |  |  | Signature of the Government Official(s):
| Firma (Signature) |  |  |  | Firma (Signature)
| Letra de Molde (Print) |  |  |  | Letra de Molde (Print)
| Firma (Signature) |  |  |  | Firma (Signature)
| Letra de Molde (Print) |  |  |  | Letra de Molde (Print)